## Executive Summary
# | Phase | Workstream | Sub-task / Deliverable | Description (what was built) | Business Value / Why | AWS Services / Components | Regions | Files / Resources | Effort / Duration | Verification Method | Risk | Status | Notes
0.1 | Network Foundation | VPC + Subnets | 3-AZ VPC (10.x.0.0/16) with 4 tiers per AZ: public, private-app, private-db, firewall. Auto-tag K8s subnets for ALB/internal-ELB discovery. | Network isolation: apps in private subnets, DB further isolated, firewall subnets for traffic inspection. Multi-AZ for HA. | VPC, Subnets, IGW | Prod (eu-west-1), Prod-DR (eu-central-1) | modules/aws-vpc + envs/<env>/vpc/ | Pre-existing | aws ec2 describe-vpcs / describe-subnets | Low | Applied (foundation) | Network Firewall configured but disabled in prod tfvars.
0.2 | Network Foundation | NAT Gateways + Internet Egress | One NAT Gateway per AZ for HA egress from private subnets. Each has its own Elastic IP. | Survives single-AZ outage without losing internet egress for private workloads. | NAT Gateway, EIP, IGW | Both | modules/aws-vpc (3 NATs per VPC) | Pre-existing | Routing tables show NAT GW as 0.0.0.0/0 target | Low | Applied (foundation) | ~$30/month per NAT per region.
0.3 | Network Foundation | VPC Endpoints | Interface endpoints for ECR (api + dkr), STS, Secrets Manager, KMS; Gateway endpoint for S3. Private DNS enabled. | Keeps high-volume AWS API traffic on the AWS backbone — lower latency, no NAT/egress cost. | VPC Endpoints (Interface + Gateway), Private DNS | Both | modules/aws-vpc | Pre-existing | aws ec2 describe-vpc-endpoints | Low | Applied (foundation)
0.4 | Network Foundation | VPC Flow Logs | All-traffic flow logs to CloudWatch Logs (7-day retention). | Network forensics + security investigation; required for SOC2/PCI. | VPC Flow Logs, CloudWatch Logs, IAM | Both | modules/aws-vpc | Pre-existing | /aws/vpc/<vpc>-flowlogs log group receives traffic | Low | Applied (foundation) | Retention should be ≥30 days for audit (currently 7).
0.5 | Network Foundation | Security Groups + NACLs | Layered SGs: app, db, RDS Proxy, EFS, jumphost. NACLs restrict DB tier to VPC-local + port 5432 from app tier. | Defence-in-depth between tiers. | Security Groups, NACLs | Both | modules/aws-vpc | Pre-existing | aws ec2 describe-security-groups | Low | Applied (foundation) | Public test SG has a hardcoded personal IP (49.207.193.197/32) — orphan, safe to clean up.
0.6 | Network Foundation | Route 53 Private Hosted Zone (RDS) | Private hosted zone for the RDS subnet group naming. | Internal DNS resolution for DB endpoints. | Route 53 | Both | modules/route53-rds-private | Pre-existing | aws route53 list-hosted-zones | Low | Applied (foundation)
1.1 | Compute Platform | EKS Cluster | Aurora-style private-endpoint EKS v1.34 cluster. Authentication mode API_AND_CONFIG_MAP. KMS-encrypted secrets. All 5 control plane log types enabled (api, audit, authenticator, controllerManager, scheduler). | Production-grade managed K8s control plane with private API and audit-quality control-plane logging. | EKS, KMS, IAM, OIDC, CloudWatch Logs | Both | modules/eks + envs/<env>/eks/ | Pre-existing | aws eks describe-cluster | Low | Applied (foundation) | Control plane log retention = 7d. Cluster deletion protection enabled.
1.2 | Compute Platform | Managed Node Group — Core | Core node group `core-ng`: m6i.xlarge instances, 1 per AZ (3 nodes total), prefix delegation enabled (max 110 pods/node), warm prefix target = 1. | Steady workload nodes for accesshub services across 3 AZs. | EKS, EC2 Auto Scaling, Launch Template | Both | modules/eks (node_group core) | Pre-existing | kubectl get nodes -L kubernetes.io/role | Low | Applied (foundation) | Currently locked at min=desired=max=1 per AZ. No auto-scaling headroom.
1.3 | Compute Platform | Managed Node Group — Spot Runners | Dedicated SPOT node group (m6a.large) with taint `workload=github-runners`. min=0, desired=1, max=3. | GitHub Actions runners on cheap spot capacity, isolated from app workloads. | EKS, EC2 Spot | Both | modules/eks (spot runner group) | Pre-existing | kubectl get nodes -l lifecycle=spot | Low | Applied (foundation)
1.4 | Compute Platform | EKS Managed Add-ons | AWS-managed addons: vpc-cni, kube-proxy, coredns, metrics-server, ebs-csi, efs-csi, amazon-cloudwatch-observability. | Cluster networking, scheduling, metrics, persistent storage, logs/observability. | EKS Managed Add-ons | Both | modules/eks (multiple aws_eks_addon blocks) | Pre-existing | aws eks list-addons --cluster-name <name> | Medium | Applied (foundation) | vpc-cni / coredns / kube-proxy versions NOT pinned in code — silent upgrades possible.
1.5 | Compute Platform | IAM Access Entries (EKS) | Modern aws_eks_access_entry resources granting AmazonEKSClusterAdminPolicy at cluster scope to specific IAM roles. | Cluster admin access for ops without legacy aws-auth ConfigMap. | IAM, EKS Access Management | Both | modules/eks (access_entry, access_policy_association) | Pre-existing | aws eks list-access-entries | Medium | Applied (foundation) | One hardcoded principal is `dev-vpc-ec2-ssm-role` — flagged for parameterization in audit.
1.6 | Compute Platform | IRSA / OIDC Provider | EKS OIDC provider linked to cluster, enabling IAM Roles for Service Accounts (IRSA) for all addons that need AWS API access. | Pods get AWS credentials without long-lived IAM keys. | IAM OIDC Provider, IAM Roles | Both | modules/eks | Pre-existing | aws iam list-open-id-connect-providers | Low | Applied (foundation)
1.7 | Compute Platform | Ubuntu Jumphost VM | EC2 instance in a private subnet with SSM-only access (no SSH port open). IAM role grants kubectl access to the private EKS API. | Bastion/admin entry point for private clusters and Aurora. | EC2, SSM, IAM | Both | modules/ubuntu-private-vm + envs/<env>/ubuntu-jumphost-vm/ | Pre-existing | aws ssm start-session --target <instance-id> | Low | Applied (foundation) | No public IP. Access only via SSM (audited).
2.1 | Data Layer (existing) | Aurora PostgreSQL Cluster — Prod | Aurora PG 16.4 cluster `prod-aurora-postgres`. KMS-encrypted (customer-managed CMK, rotated). Multi-AZ writer + reader. Backups 7d. Performance Insights + Enhanced Monitoring (60s). PostgreSQL audit logs exported to CloudWatch. | Production database for accesshub workloads with HA, encryption, and observability. | Aurora RDS, KMS, CloudWatch Logs | Prod (eu-west-1) | modules/aurora-postgres + envs/prod/eu-west-1/aurora-postgres/ | Pre-existing | aws rds describe-db-clusters | Low | Applied (foundation) | Originally db.t4g.medium — being upgraded to db.r6g.large for Global DB eligibility (Workstream 15).
2.2 | Data Layer (existing) | RDS Proxy — Prod | RDS Proxy in front of Aurora with TLS required, Secrets Manager auth, and enforce_rds_proxy_only=true (DB SG locked down to proxy ingress only). | Connection pooling + credential rotation handling + IAM identity layer for DB access. | RDS Proxy, IAM, Secrets Manager, Security Groups | Prod (eu-west-1) | modules/aurora-postgres (proxy block) | Pre-existing | aws rds describe-db-proxies | Low | Applied (foundation)
2.3 | Data Layer (existing) | Aurora PostgreSQL Cluster — Prod-DR (standalone, pre-DR-work) | Aurora PG 16.4 cluster `prod-dr-aurora-postgres` as a STANDALONE database in eu-central-1. Separate KMS CMK, separate secret, deletion_protection=false (now being fixed). | Originally provisioned as DR-region placeholder. NOT linked to prod — separate empty DB. | Aurora RDS, KMS, RDS Proxy, Secrets Manager | Prod-DR (eu-central-1) | envs/prod-dr/eu-central-1/aurora-postgres/ | Pre-existing | aws rds describe-db-clusters | Medium | Applied (foundation) | Being replaced by Aurora Global DB secondary member (Workstream 16). Original was misleading — same module config but no data link to prod.
2.4 | Data Layer (existing) | Aurora Secrets — Both Regions | Master credentials stored in AWS Secrets Manager: `prod/aurora/app-credentials` and `prod-dr/aurora/app-credentials`. Same username, same password (manually synced). | RDS Proxy authenticates against the cluster using these secrets. | Secrets Manager | Both | Manual creation (aws secretsmanager create-secret) | Pre-existing | aws secretsmanager get-secret-value | Low | Applied (foundation) | Manual sync of password across regions = drift risk. Future enhancement: enable Secrets Manager cross-region replication.
3.1 | Storage Layer (existing) | Data EFS (per region, pre-replication) | Encrypted EFS file system created by the EKS module. Mount targets in each private app subnet. AWS Backup policy enabled. | Shared persistent storage for accesshub pods (uploads, schema files, auth files, login auth sources, etc.). | EFS, EFS Mount Targets, KMS, AWS Backup | Both | modules/eks (EFS block) | Pre-existing | aws efs describe-file-systems | Low | Applied (foundation) | Prod-DR standalone data EFS replaced by replicated EFS (Workstream 10).
3.2 | Storage Layer (existing) | EFS Dynamic StorageClass | Kubernetes StorageClass `efs-sc` configured for dynamic Access Point provisioning per PVC. ReadWriteMany support. | Apps request storage via PVC; CSI driver creates an EFS Access Point per request. | Kubernetes CSI, EFS | Both | envs/<env>/eks/k8s/efs-storageclass.yaml | Pre-existing | kubectl get sc efs-sc | Medium | Applied (foundation) | Works on writable EFS in prod. Replaced by static PV in prod-dr (Workstream 12) for read-only replica.
4.1 | Observability + Add-ons | AWS Load Balancer Controller | Helm chart pinned to 1.7.2. IRSA role with ALB-controller managed policy. 2 replicas. Creates ALBs from K8s Ingress resources. | Cluster-native HTTPS ingress. | EKS, ALB, IAM, Helm | Both | modules/eks-alb-controller + envs/<env>/eks-add-on/alb-controller/ | Pre-existing | kubectl get pods -n kube-system -l app.kubernetes.io/name=aws-load-balancer-controller | Low | Applied (foundation) | Missing PDB and resource limits in current config.
4.2 | Observability + Add-ons | ALB Access Logs to S3 | Dedicated S3 bucket per region for ALB access logs with bucket policy granting logdelivery.elasticloadbalancing.amazonaws.com PutObject. | Web-tier audit trail for security investigations. | ALB, S3 | Both | envs/<env>/eks-add-on/alb-controller (bucket resources) | Pre-existing | aws s3 ls s3://prod-accesshub-alb-access-logs-*/ | Low | Applied (foundation) | Ingress annotation must be set on each app's Ingress.
4.3 | Observability + Add-ons | External Secrets Operator (ESO) | Helm-deployed ESO with ClusterSecretStore pointing to AWS Secrets Manager. JWT (IRSA) auth. | K8s secrets sync from Secrets Manager — no static secrets in YAML/git. | EKS, IRSA, Secrets Manager | Both | modules/eks-eso + envs/<env>/eks-add-on/external-secrets/ | Pre-existing | kubectl get clustersecretstore | High | Applied (foundation) | IAM policy uses wildcard `*` for secret ARNs — flagged in audit as critical. Tighten before adding more secrets.
4.4 | Observability + Add-ons | Argo CD (GitOps) | Helm-deployed Argo CD with ECR-mirrored images. Tracks helm-charts directory for accesshub deployments. | GitOps deployment automation — values files in git are the source of truth. | EKS, Helm, GitOps | Both | modules/eks-argocd + envs/<env>/eks-add-on/argocd/ | Pre-existing | argocd app list | High | Applied (foundation) | Currently HTTP-only (server.insecure=true), internet-facing without TLS — flagged critical in audit. Needs SSO + TLS.
4.5 | Observability + Add-ons | Velero (Backups) | Helm-deployed Velero. Dedicated S3 backup bucket with customer-managed KMS, versioning, lifecycle. IAM scoped by cluster tag. Daily backup schedule with 7-day TTL. | Cluster state + PV snapshots for disaster recovery. | EKS, S3, KMS, IAM, EBS Snapshots | Both | modules/eks-velero + envs/<env>/eks-add-on/velero/ | Pre-existing | velero backup get | Low | Applied (foundation) | Excellent prod-grade configuration. Missing alerts on backup failure.
4.6 | Observability + Add-ons | Amazon Managed Prometheus (AMP) | AMP workspace + AMP-managed scraper for the cluster. Selective metric relabeling (accesshub namespace only, CPU/mem/network only). | Long-term metrics storage without self-hosted Prometheus. | AMP, EKS | Both | envs/<env>/eks-add-on/managed-prometheus/ | Pre-existing | aws amp list-workspaces | Low | Applied (foundation) | No alerting rules yet.
4.7 | Observability + Add-ons | Grafana | Self-hosted Grafana with IRSA-based AMP datasource (SigV4 auth). Dashboard sidecar for loading from monitoring namespace. | Dashboarding for AMP metrics. | EKS, Helm, AMP | Both | modules/eks-grafana + envs/<env>/eks-add-on/grafana/ | Pre-existing | kubectl get ingress -n monitoring | High | Applied (foundation) | Persistence disabled, public ingress without auth — flagged critical. Plan to migrate to AWS Managed Grafana.
4.8 | Observability + Add-ons | Node Monitoring (kube-state-metrics + node-exporter) | Helm-deployed kube-state-metrics + node-exporter. Versions pinned. ECR-mirrored images. | Cluster + node-level metrics exported to Prometheus. | EKS, Helm | Both | modules/eks-node-monitoring + envs/<env>/eks-add-on/node-monitoring/ | Pre-existing | kubectl get pods -n monitoring | Low | Applied (foundation)
4.9 | Observability + Add-ons | CloudWatch Observability addon (Container Insights) | EKS managed addon: amazon-cloudwatch-observability. Deploys Fluent Bit + CloudWatch Agent DaemonSets to ship pod logs + node metrics. | Pod stdout → CloudWatch Logs (foundation for SIEM pipeline). | EKS, CloudWatch Agent, Fluent Bit | Both | modules/eks (cloudwatch_observability addon block) | Pre-existing | kubectl get pods -n amazon-cloudwatch | Low | Applied (foundation) | Foundation for SIEM Log Pipeline (Workstream 7).
5.1 | CI/CD | GitHub OIDC Provider + Role | IAM OIDC provider for token.actions.githubusercontent.com. GitHub deploy role with repo-scoped trust policy. | GitHub Actions deploys to AWS without long-lived IAM keys. | IAM OIDC, GitHub Actions | Both | modules/github-oidc-provider, modules/github-oidc-role | Pre-existing | aws iam list-open-id-connect-providers | Low | Applied (foundation)
5.2 | CI/CD | GitHub Runners (EKS-hosted) | Self-hosted GitHub runners on spot nodes (taint=workload=github-runners). | Faster CI/CD with cluster-local network access; spot pricing. | EKS, EC2 Spot, GitHub Actions | Both | modules/github-runners | Pre-existing | GitHub Actions runner pool status | Low | Applied (foundation)
6.1 | Application Layer | Accesshub Helm Chart | Main Helm chart with 15+ Deployments (admin, gateway, login, scim, pg, snow, scheduler, GRC, etc.), Services, Ingress backend + frontend, ConfigMaps, ExternalSecrets, PDBs, ServiceAccounts, ClusterSecretStore. | Single source of truth for accesshub workload deployment via ArgoCD. | Kubernetes, Helm, ArgoCD | Both via Helm values per env | helm-charts/helm/accesshub/ | Pre-existing | kubectl get pods -n accesshub | Medium | Applied (foundation) | Recent changes in Workstream 17 fixed config drift between prod and prod-dr values.
6.2 | Application Layer | Init Containers (Data Seeders) | 4 idempotent init containers: seed-target-app-resources, seed-schema-assets, seed-accesshub-files, seed-auth-files. Each copies from container image to EFS subPath only if empty. | First-run data bootstrap for shared file systems. | Kubernetes | Both | helm-charts/helm/accesshub/templates/deployment.yaml | Pre-existing | kubectl logs <pod> -c seed-* | Low | Applied (foundation) | Designed to be safe on read-only EFS (skip cp when destination non-empty).
6.3 | Application Layer | DB Migration Job | Helm chart Job that runs DB schema migrations against the cluster's Aurora via RDS Proxy. | Schema-aware deploys; enable_dbmigration flag in values. | Kubernetes Job, Aurora | Both | helm-charts/helm/accesshub/templates/db-migration-job.yaml | Pre-existing | kubectl get jobs -n accesshub | Medium | Applied (foundation)
6.4 | Application Layer | Tenant Bootstrap Job | Helm chart Job for initial tenant onboarding. | One-off setup task on cluster bring-up. | Kubernetes Job | Both | helm-charts/helm/accesshub/templates/tenant-bootstrap-job.yaml | Pre-existing | kubectl get jobs -n accesshub | Low | Applied (foundation)
6.5 | Application Layer | Health Aggregator | Separate Python service (Helm subchart) aggregating health status across accesshub microservices. Exposed via own Ingress. | Single endpoint for monitoring tools to query overall system health. | Kubernetes, Python, ALB | Both | helm-charts/health-aggregator/ + helm chart templates | Pre-existing | curl https://prod-aws.accesshub-identity.com/health | Low | Applied (foundation)
7.1 | SIEM Log Pipeline (recent) | Module + pipeline build | Built modules/security-log-pipeline: KMS CMK, S3 bucket with versioning/BPA/KMS-SSE/lifecycle/TLS-only/unencrypted-PUT deny, least-priv IAM roles, Firehose + CW subscription filters. | Centralized security log archive supporting SIEM tooling, compliance retention, incident forensics. | S3, KMS, IAM, Kinesis Firehose, CloudWatch Logs | Prod (eu-west-1) | 3 module files + 7 env files | ~6 hr design + build | S3 objects landing under eks/cluster=...source=application/year=.../... | Low | Applied
7.2 | SIEM Log Pipeline (recent) | EKS audit log subscription | Second Firehose + subscription filter on /aws/eks/<cluster>/cluster log group (filter: {$.kind = "Event" && $.apiVersion = "audit.k8s.io/v1"}). | Persistent audit trail of K8s API operations for compliance. | Kinesis Firehose, CloudWatch Logs | Prod (eu-west-1) | Single map entry in tfvars | Included in 7.1 | Audit events appear in S3 audit/cluster=... prefix | Low | Applied
8.1 | ACM Certificates (recent) | Reusable ACM cert module — Prod | Built modules/acm-public-cert: DNS validation, key_algorithm guard, Route53 validation records, create_before_destroy lifecycle. | TLS termination for prod ALB serving prod-aws.accesshub-identity.com with auto-renewal. | ACM, Route53 | Prod (eu-west-1) | 3 module files + 6 env files | ~3 hr | ACM cert status ISSUED | Low | Applied | RSA_2048 explicit. SAN list parameterised.
8.2 | ACM Certificates (recent) | Regional cert — Prod-DR | envs/prod-dr/eu-central-1/acm/accesshub-identity reuses prod module; regional cert for same FQDN. | Prod-DR ALB needs its own regional cert to serve HTTPS post-failover. | ACM, Route53 | Prod-DR (eu-central-1) | 6 new env files (zero new module code) | <1 hr | Cert status ISSUED in eu-central-1 | Low | Pending apply | Same FQDN: DNS flip Lambda at failover doesn't need to change TLS chain.
9.1 | EKS Module — DR refactors (recent) | create_efs_file_system variable | Made data EFS resources (file system, mount targets, SG, backup policy) conditional on a new variable. Default true (backward compatible). | Allows prod-dr EKS to skip its own data EFS so it can consume the replicated one. | EKS, EFS | Shared module + Prod-DR (eu-central-1) | 2 files modified | <1 hr | Prod EKS plan shows no changes; prod-dr destroys local data EFS | Medium | Applied
9.2 | EKS Module — DR refactors (recent) | create_efs_logs_file_system variable + logs EFS | Added a SECOND EFS for logs with its own SG, mount targets, backup policy. Always region-local, never replicated. | Warm-standby pods in prod-dr write logs locally even when data EFS is read-only. | EFS, EC2 Security Groups | Both | modules/eks: 3 files modified; env: 4 files | ~2 hr | kubectl get pvc efs-logs-claim returns Bound | Low | Applied | Critical for warm-standby. K8s manifests added (Workstream 11).
10.1 | EFS Cross-Region Replication (recent) | Replication primitive + DR infra | Built modules/efs-replication wrapping aws_efs_replication_configuration. Env stack creates KMS CMK + mount targets + SG in eu-central-1 via provider alias. | Sub-minute RPO data replication from prod EFS to prod-dr. | EFS Replication, KMS, EC2 SG | Both | 3 module files + 7 env files | ~4 hr | Replication ENABLED, lag <1s | Medium | Pending apply | Destination EFS auto-created by AWS, we manage only replication config + network resources.
11.1 | EFS Logs Split — K8s + Helm (recent) | Logs SC + PVC (both regions) | Added efs-logs-storageclass.yaml + efs-logs-pvc.yaml in both eks/k8s/ folders. PVC efs-logs-claim binds to the writable logs EFS. | In-cluster handle for /app/log mount on logs EFS. | Kubernetes CSI, EFS | Both | 4 new YAML files | <5 min apply per region | kubectl get pvc efs-logs-claim Bound | Low | Applied
11.2 | EFS Logs Split — K8s + Helm (recent) | Helm values repointing | persistentLogs.claimName: efs-claim → efs-logs-claim in both values-prod.yaml and values-prod-dr.yaml. | Apps write logs to new logs EFS without app/mount-path change. | Helm | Both | 2 helm files modified | <5 min commit + ArgoCD reconcile | Pod shared-logs volume backed by efs-logs-claim | Low | Applied
12.1 | Prod-DR Static PV (recent) | Static PV+PVC for replicated EFS | Rewrote envs/prod-dr/eu-central-1/eks/k8s/efs-pvc.yaml as static PV+PVC using volumeHandle: fs-XXX::fsap-YYY. ReadWriteMany — failover transition needs no manifest change. | Dynamic provisioning fails on read-only replica; static PV references existing Access Point. | Kubernetes CSI, EFS Access Points | Prod-DR (eu-central-1) | 2 files modified | <1 hr design + write | PVC efs-claim Bound; pod reads from /app/... | Low | Pending K8s apply | Requires manual Access Point creation on replica (one-time CLI). Same manifest survives failover.
13.1 | Aurora Module — Global DB (recent) | is_secondary + global_cluster_identifier vars | Module accepts is_secondary + global_cluster_identifier. When secondary, master_*/database_name are null (inherited from global cluster's primary). | Same module provisions both primaries (existing) and Global DB secondaries (new). | Aurora RDS | Shared module | modules/aurora-postgres: 2 files | ~2 hr | Prod plan no-op; prod-dr plan creates secondary | Low | Applied | Precondition: is_secondary requires global_cluster_identifier.
13.2 | Aurora Module — Global DB (recent) | lifecycle.ignore_changes on global_cluster_identifier | Prevents Terraform from destroying prod cluster when Global Cluster adopts it via source_db_cluster_identifier. | Safety: protects existing prod data during Global DB enablement. | Aurora RDS, Terraform lifecycle | Shared module | modules/aurora-postgres/main.tf | <30 min | Prod plan: cluster NOT marked for replacement | Low | Applied
13.3 | Aurora Module — Global DB (recent) | replace_triggered_by on RDS Proxy target | Lifecycle rule causes proxy target to recreate when cluster is replaced (Workstream 16). | Without this, proxy stays attached to phantom cluster after Phase 7. | RDS Proxy, Terraform lifecycle | Shared module | modules/aurora-postgres/main.tf | <15 min | Prod-DR Phase 7 plan: proxy target as -/+ replace | Low | Applied
14.1 | Aurora Global Cluster (recent) | New global cluster env stack | envs/prod/eu-west-1/aurora-postgres-global creates aws_rds_global_cluster with source_db_cluster_identifier referencing prod cluster ARN. | Online adoption of prod into Global DB — no recreation, foundation for cross-region replication. | Aurora Global Database | Global resource (eu-west-1) | 7 new files | ~1 hr | describe-global-clusters shows prod as writer member | Low | Pending apply
15.1 | Prod Aurora — Instance Class Upgrade (recent) | db.t4g.medium → db.r6g.large | Tfvars change. Aurora rolls readers first, then failover-and-upgrade writer. | t-class NOT eligible for Aurora Global DB; r6g.large is the smallest eligible class (Graviton, best perf/cost). | Aurora RDS, EC2 | Prod (eu-west-1) | 1 tfvars line modified | 5–10 min + ~30-60s app blip | Both instances db.r6g.large, available | Medium | Pending apply | Cost delta ~$300/mo additional in prod. RDS Proxy + app retry handles blip.
16.1 | Prod-DR Aurora → Secondary (recent) | Destroy standalone, recreate as Global DB member | Tfvars: is_secondary=true, global_cluster_identifier, instance_class=db.r6g.large, deletion_protection=true. | Replaces empty standalone prod-dr with a member of the Global Cluster. Bootstraps from prod's storage. | Aurora Global DB, RDS Proxy | Prod-DR (eu-central-1) | 3 files modified | 15–25 min (cross-region bootstrap) | 2 members in global cluster; prod-dr IsWriter=false | Medium | Pending apply | Destructive on prod-dr (empty per pre-flight). Proxy auto-rebinds via replace_triggered_by.
17.1 | Helm Chart Fixes (recent) | authFilesPersistence — fix prod-dr drift | Added 5-line authFilesPersistence block to values-prod-dr.yaml (was missing — pre-existing drift bug). | Auth files now correctly mounted in prod-dr; apps depending on them won't fail at runtime. | Helm | Prod-DR | 1 helm file modified | <15 min | diff between prod/prod-dr values shows 6 identical persistence sections | Low | Applied
17.2 | Helm Chart Fixes (recent) | persistentLogs claim repoint (both) | Both values files: persistentLogs.claimName → efs-logs-claim. | Apps in both regions write logs to new region-local writable logs EFS. | Helm | Both | 2 helm files modified | Combined with 11.2 | Pod's shared-logs volume = PVC efs-logs-claim | Low | Applied
18.1 | Failover Automation (planned) | EFS failover Lambda | Lambda that calls efs:DeleteReplicationConfiguration → replica EFS becomes writable. | Step 1 of failover sequence — frees up persistent storage. | Lambda, EFS | eu-west-1 (operates on prod's EFS) | Designed, no code yet | Est. ~4 hr build | Replica EFS LifeCycleState becomes 'available' (not 'replicating') | Medium | Designed (not built) | Irreversible. Step 1 of SSM runbook.
18.2 | Failover Automation (planned) | Aurora failover Lambda | Lambda that calls rds:FailoverGlobalCluster (planned) or rds:RemoveFromGlobalCluster (disaster) → prod-dr becomes writer. | Step 2 of failover sequence — promotes DB. | Lambda, Aurora | eu-west-1 (managed) or eu-central-1 (detach) | Designed, no code yet | Est. ~4 hr build | Global cluster members: prod-dr IsWriter=true | Medium | Designed (not built) | Managed failover reversible; detach irreversible.
18.3 | Failover Automation (planned) | Node group scale-up Lambda | Lambda that calls eks:UpdateNodegroupConfig → desired_size 0 → 3 in prod-dr. | Step 3 — bring up compute capacity. | Lambda, EKS | eu-central-1 | Designed, no code yet | Est. ~4 hr build (incl. EKS module refactor for ignore_changes on desired_size) | Node group status ACTIVE with desired=3 | Medium | Designed (not built) | Requires EKS module: expose scaling vars + ignore_changes on scaling_config.desired_size.
18.4 | Failover Automation (planned) | App replicas scale-up Lambda | Lambda that uses GitHub API to commit values-prod-dr.yaml: replicaCount 0→3. ArgoCD reconciles. | Step 4 — scale up app pods. | Lambda, GitHub API, ArgoCD | External (commits to git) | Designed, no code yet | Est. ~6 hr build (incl. GitHub PAT in Secrets Manager) | kubectl get deployment -n accesshub shows REPLICAS=3, READY=3 | Medium | Designed (not built) | GitHub PAT with Contents:Write scope on the repo.
18.5 | Failover Automation (planned) | DNS flip Lambda | Lambda that calls route53:ChangeResourceRecordSets → prod-aws.accesshub-identity.com flipped from prod ALB to prod-dr ALB. | Step 5 (final) — redirect user traffic. | Lambda, Route 53 | External (global) | Designed, no code yet | Est. ~3 hr build | dig prod-aws.accesshub-identity.com points to eu-central-1 ALB | Medium | Designed (not built) | TLS termination handed off to prod-dr regional ACM cert (Workstream 8.2).
18.6 | Failover Automation (planned) | SSM Runbook (AccessHubDRFailover) | AWS Systems Manager Automation document orchestrating the 5 Lambdas in order, with safety Confirm parameter. | Single human-initiated entry point. Audit trail via CloudTrail. | SSM Automation, Lambda, SNS | External (initiated from anywhere) | Designed, no code yet | Est. ~6 hr build + dry-run testing | aws ssm start-automation-execution succeeds end-to-end with dry-run mode | Medium | Designed (not built) | Operator runs the runbook; runbook fires Lambdas.
19.1 | CI/CD Pipeline DR Updates (recent) | Image build pipeline — push to prod-dr ECR | Extended .github/workflows/build-from-app-repo.yml: when source_branch=prod, the same locally-built image (built once) is now tagged and pushed to THREE registries — dev (skipped for prod branch), prod (eu-west-1 ECR), AND prod-dr (eu-central-1 ECR). Added 3 new workflow steps: Configure AWS Credentials (prod DR) + Log in to Amazon ECR (prod DR) + Push image (prod DR). | Both regions need identical container images so failover doesn't require image re-build. Single build pipeline pushes to both ECRs maintaining image SHA parity. | GitHub Actions, AWS ECR, IAM OIDC | Prod + Prod-DR ECRs | .github/workflows/build-from-app-repo.yml — 3 new steps per matrix service (11 services) | ~3 hr build + test | AWS ECR (eu-central-1) shows accesshub/<service>:sha-<commit> for all 11 services with same digest as eu-west-1. | Low | Applied | Single docker build, tagged and pushed to both regions — keeps image digests identical.
19.2 | CI/CD Pipeline DR Updates (recent) | Image build pipeline — dual values file update | Extended update-helm-digests job in build-from-app-repo.yml: when source_branch=prod, VALUES_FILES is now "helm/accesshub/values-prod.yaml,helm/accesshub/values-prod-dr.yaml" (comma-separated). Python script iterates over both files and writes the same digest to each, ensuring prod and prod-dr stay version-locked. | Both regions deploy the SAME image SHA via ArgoCD — eliminates drift between regional environments. | GitHub Actions, Helm | Both | .github/workflows/build-from-app-repo.yml (update-helm-digests job — Python loop over VALUES_FILES split) | ~1 hr | git log shows commit "chore: update signed image digests" with both prod values files modified together. | Low | Applied | Single commit to git per build keeps both regions in sync.
19.3 | CI/CD Pipeline DR Updates (recent) | Health aggregator pipeline — DR ECR push | build-health-aggregator.yml: added prod-dr ECR Configure Credentials + Login + Push steps (same pattern as 19.1). Triggers on push to dev/prod/main branches with paths filter on health-aggregator/. | Health aggregator service is built and shipped to both ECRs. | GitHub Actions, AWS ECR | Prod + Prod-DR ECRs | .github/workflows/build-health-aggregator.yml — 3 new steps | ~1 hr | ECR eu-central-1 shows accesshub/health-aggregator:sha-<commit>. | Low | Applied
19.4 | CI/CD Pipeline DR Updates (recent) | Health aggregator pipeline — dual values update | Updated VALUES_FILES env in build-health-aggregator.yml: for prod branches, list is "helm/accesshub/values-health-prod.yaml,helm/accesshub/values-health-prod-dr.yaml". Python loop writes digest to both. | Health aggregator stays version-locked across regions. | GitHub Actions, Helm | Both | .github/workflows/build-health-aggregator.yml (update step) | <30 min | Both health values files updated in single commit. | Low | Applied
19.5 | CI/CD Pipeline DR Updates (recent) | Tenant bootstrap workflow — prod_dr ArgoCD target | run-tenant-bootstrap.yml: env_type choice now includes dev/prod/prod_dr. When env_type=prod, the workflow runs tenant bootstrap on BOTH the prod ArgoCD app (accesshub-prod-tenant-bootstrap) AND the prod_dr ArgoCD app (accesshub-prod-dr-tenant-bootstrap). When env_type=prod_dr, runs only on prod_dr cluster. Uses new ARGOCD_SERVER_PROD_DR + ARGOCD_AUTH_TOKEN_PROD_DR secrets. | Operator can run tenant bootstrap on both regions in one workflow invocation, ensuring tenant state is identical. | GitHub Actions, ArgoCD CLI | Both EKS clusters | .github/workflows/run-tenant-bootstrap.yml — env_type choice expanded; ArgoCD config switched to per-target | ~2 hr | argocd app sync on both target clusters returns Synced + Healthy. | Low | Applied | Read gatewaysvc digest from each region's values file; ensures correct image used per cluster.
19.6 | CI/CD Pipeline DR Updates (recent) | Base image mirroring — prod-dr variant | Added helm-charts/scripts/mirror-health-aggregator-base-to-ecr-prod-dr.sh (and reused mirror-base-images-to-ecr.sh with region override) to mirror third-party base images (maven, eclipse-temurin, python) into the prod-dr ECR. Without this, prod-dr ECR can't serve as a base-image source. | Base images (FROM lines in Dockerfiles) reference an ECR via the BASE_REGISTRY ARG. Both prod and prod-dr ECRs must have the same base images mirrored so cross-region builds + pulls work. | AWS ECR, Docker (manual or scheduled mirror) | Prod-DR (eu-central-1) ECR | helm-charts/scripts/mirror-health-aggregator-base-to-ecr-prod-dr.sh (50 lines); mirror-base-images-to-ecr.sh accepts region argument | ~1 hr per script + ~30 min mirror runs | aws ecr list-images --repository-name thirdparty/maven --region eu-central-1 shows the expected tags. | Low | Applied | Currently manual run; can be scheduled or moved into pipeline if base images update frequently.
19.7 | CI/CD Pipeline DR Updates (recent) | Dockerfile BASE_REGISTRY pattern (existing, verified DR-compatible) | Reviewed all 11 service Dockerfiles + health-aggregator Dockerfile. Pattern: `ARG BASE_REGISTRY=<default>` followed by `FROM ${BASE_REGISTRY}/thirdparty/...`. Pipeline overrides BASE_REGISTRY at build time based on which ECR is logged in. Default value pinned to existing ECR for local-build fallback. | Single Dockerfile works for both regions because BASE_REGISTRY is parameterised. Verified pattern is correct across all 11 services + health-aggregator. | Docker, ECR | Build-time concern | helm-charts/docker/services/Dockerfile.* (11 files), helm-charts/docker/frontend/dockerfile, helm-charts/docker/db-migration/Dockerfile.dbmigration, helm-charts/health-aggregator/Dockerfile | ~1 hr review | grep -l "ARG BASE_REGISTRY" Dockerfile.* shows all files use the pattern. | Low | Applied | If any new Dockerfile is added, ensure it follows the same ARG BASE_REGISTRY pattern.
19.8 | CI/CD Pipeline DR Updates (recent) | GitHub secrets — new DR secrets | Added new repository secrets for prod-dr region operations: AWS_ROLE_TO_ASSUME_PROD_DR (IAM role for ECR push), AWS_REGION_PROD_DR (eu-central-1), ARGOCD_SERVER_PROD_DR (DR ArgoCD endpoint), ARGOCD_AUTH_TOKEN_PROD_DR (DR ArgoCD JWT). | Pipelines need credentials for prod-dr region — without these, the new prod-dr steps would fail at OIDC/ArgoCD auth. | GitHub Actions Secrets, IAM OIDC, ArgoCD | Both | GitHub repository settings (4 new secrets) | <30 min | Workflow run logs show successful ECR login + push to eu-central-1, ArgoCD sync on prod_dr cluster. | Low | Applied | Token rotation policy should match the prod equivalents (e.g., ArgoCD JWT renewal cadence).

## Legend
Status | Meaning
Applied | Code deployed to AWS in this engagement and verified working
Applied (foundation) | Pre-existing infrastructure deployed before this engagement — listed for completeness
Pre-existing | Same as 'Applied (foundation)' — already in place
Code complete | In git, awaiting maintenance window for apply
Pending apply | Terraform code ready, needs `terraform apply`
Pending K8s apply | Kubernetes manifests ready, needs `kubectl apply`
Designed (not built) | Architecture designed, no code yet
In progress | Active troubleshooting or partial completion
Risk | Meaning
Low | Additive change, no downtime, easy rollback
Medium | Brief app blip possible, or contained scope destruction (e.g., empty standalone cluster)
High | Data-affecting change requiring planned rollback procedure
Phase | Description
0. Network Foundation | VPC, subnets, NATs, security groups, flow logs, VPC endpoints — pre-existing
1. Compute Platform | EKS cluster, node groups, addons, IRSA, jumphost — pre-existing
2. Data Layer (existing) | Aurora clusters and RDS Proxy in both regions, master secrets — pre-existing
3. Storage Layer (existing) | Data EFS per region with dynamic provisioning — pre-existing
4. Observability + Add-ons | ALB Controller, ESO, Argo CD, Velero, AMP, Grafana, node monitoring, Container Insights — pre-existing
5. CI/CD | GitHub OIDC + runners on EKS — pre-existing
6. Application Layer | Accesshub Helm chart, init containers, jobs, health aggregator — pre-existing
7. SIEM Log Pipeline | RECENT — built in this engagement: CW Logs → Firehose → S3 lake
8. ACM Certificates | RECENT — public ACM certs in both regions for transparent DR
9. EKS Module DR refactors | RECENT — module enhancements to support cross-region EFS replication + logs split
10. EFS Cross-Region Replication | RECENT — continuous replica from prod EFS to prod-dr
11. EFS Logs Split (K8s + Helm) | RECENT — region-local writable logs EFS while data EFS is replicated
12. Prod-DR Static PV | RECENT — static PV+PVC for read-only replica EFS via Access Point
13. Aurora Module — Global DB support | RECENT — module enhancements for Aurora Global Database
14. Aurora Global Cluster | RECENT — new global cluster adopting prod as primary
15. Prod Aurora Instance Class Upgrade | RECENT — t4g.medium → r6g.large (Global-DB-eligible)
16. Prod-DR Aurora → Secondary | RECENT — destroy standalone, recreate as secondary of Global DB
17. Helm Chart Fixes | RECENT — config drift fixes + logs claim repointing
18. Failover Automation | PLANNED — 5 Lambdas + SSM runbook to orchestrate DR failover
19. CI/CD Pipeline DR Updates | RECENT — GitHub Actions workflows + base image mirror scripts adapted for prod-dr ECR + dual region values file updates

## File Inventory
# | Workstream | Path | Type | Purpose
1 | 7. SIEM Log Pipeline | modules/security-log-pipeline/main.tf | New | KMS CMK, S3 bucket, IAM, Firehose, CW subscription filters
2 | 7. SIEM Log Pipeline | modules/security-log-pipeline/variables.tf | New | Module inputs
3 | 7. SIEM Log Pipeline | modules/security-log-pipeline/outputs.tf | New | Module outputs
4 | 7. SIEM Log Pipeline | envs/prod/eu-west-1/security/log-pipeline/ | New | Env stack wiring (7 files)
5 | 8. ACM Cert (Prod) | modules/acm-public-cert/main.tf | New | Cert + Route53 validation + wait
6 | 8. ACM Cert (Prod) | modules/acm-public-cert/variables.tf | New | Module inputs
7 | 8. ACM Cert (Prod) | modules/acm-public-cert/outputs.tf | New | ARN + validation FQDNs
8 | 8. ACM Cert (Prod) | envs/prod/eu-west-1/acm/accesshub-identity/ | New | Env stack for prod cert
9 | 8. ACM Cert (Prod-DR) | envs/prod-dr/eu-central-1/acm/accesshub-identity/ | New | Env stack — regional cert in eu-central-1
10 | 9. EKS Module DR refactors | modules/eks/variables.tf | Modified | create_efs_file_system + create_efs_logs_file_system + EFS logs config
11 | 9. EKS Module DR refactors | modules/eks/main.tf | Modified | Conditional data EFS + new logs EFS block (SG, mount targets, backup policy)
12 | 9. EKS Module DR refactors | modules/eks/outputs.tf | Modified | efs_logs_file_system_id + efs_logs_security_group_id
13 | 9. EKS Module DR refactors | envs/prod/eu-west-1/eks/main.tf | Modified | Enable logs EFS
14 | 9. EKS Module DR refactors | envs/prod/eu-west-1/eks/outputs.tf | Modified | Expose logs EFS IDs
15 | 9. EKS Module DR refactors | envs/prod-dr/eu-central-1/eks/main.tf | Modified | create_efs_file_system=false + enable logs EFS
16 | 9. EKS Module DR refactors | envs/prod-dr/eu-central-1/eks/outputs.tf | Modified | Expose logs EFS IDs
17 | 10. EFS Cross-Region Replication | modules/efs-replication/main.tf | New | aws_efs_replication_configuration
18 | 10. EFS Cross-Region Replication | modules/efs-replication/variables.tf | New | Inputs
19 | 10. EFS Cross-Region Replication | modules/efs-replication/outputs.tf | New | Destination EFS attrs
20 | 10. EFS Cross-Region Replication | envs/prod/eu-west-1/efs-replication/ | New | Env stack: KMS + replication + SG + mount targets (cross-region)
21 | 11. EFS Logs Split K8s | envs/prod/eu-west-1/eks/k8s/efs-logs-storageclass.yaml | New | SC for prod logs EFS
22 | 11. EFS Logs Split K8s | envs/prod/eu-west-1/eks/k8s/efs-logs-pvc.yaml | New | PVC efs-logs-claim
23 | 11. EFS Logs Split K8s | envs/prod-dr/eu-central-1/eks/k8s/efs-logs-storageclass.yaml | New | SC for prod-dr logs EFS
24 | 11. EFS Logs Split K8s | envs/prod-dr/eu-central-1/eks/k8s/efs-logs-pvc.yaml | New | PVC efs-logs-claim
25 | 11. EFS Logs Split Helm | helm-charts/helm/accesshub/values-prod.yaml | Modified | persistentLogs claim updated
26 | 11. EFS Logs Split Helm | helm-charts/helm/accesshub/values-prod-dr.yaml | Modified | persistentLogs claim updated; authFilesPersistence added
27 | 12. Prod-DR Static PV | envs/prod-dr/eu-central-1/eks/k8s/efs-pvc.yaml | Rewritten | Static PV+PVC via Access Point handle (RWX)
28 | 12. Prod-DR Static PV | envs/prod-dr/eu-central-1/eks/k8s/efs-storageclass.yaml | Modified | Kept for reference only
29 | 13. Aurora Module DR | modules/aurora-postgres/variables.tf | Modified | is_secondary, global_cluster_identifier
30 | 13. Aurora Module DR | modules/aurora-postgres/main.tf | Modified | Conditional master_*/db_name; lifecycle.ignore_changes; replace_triggered_by
31 | 14. Aurora Global Cluster | envs/prod/eu-west-1/aurora-postgres-global/ | New | Env stack creating aws_rds_global_cluster
32 | 15. Prod Aurora Instance Class | envs/prod/eu-west-1/aurora-postgres/terraform.tfvars | Modified | db.t4g.medium → db.r6g.large
33 | 16. Prod-DR Aurora → Secondary | envs/prod-dr/eu-central-1/aurora-postgres/terraform.tfvars | Modified | is_secondary, global_cluster_identifier, instance_class, deletion_protection
34 | 16. Prod-DR Aurora → Secondary | envs/prod-dr/eu-central-1/aurora-postgres/main.tf | Modified | Pass new vars to module
35 | 16. Prod-DR Aurora → Secondary | envs/prod-dr/eu-central-1/aurora-postgres/variables.tf | Modified | Declare new env vars
36 | 19. CI/CD Pipeline DR Updates | .github/workflows/build-from-app-repo.yml | Modified | Added prod-dr ECR push steps (3 new); update-helm-digests now writes to both values-prod.yaml + values-prod-dr.yaml
37 | 19. CI/CD Pipeline DR Updates | .github/workflows/build-health-aggregator.yml | Modified | Added prod-dr ECR push steps; dual values-health update
38 | 19. CI/CD Pipeline DR Updates | .github/workflows/run-tenant-bootstrap.yml | Modified | env_type choice extended (dev/prod/prod_dr); prod runs both clusters; new ARGOCD_*_PROD_DR secrets used
39 | 19. CI/CD Pipeline DR Updates | helm-charts/scripts/mirror-health-aggregator-base-to-ecr-prod-dr.sh | New | Mirror base images to eu-central-1 ECR for prod-dr
40 | 19. CI/CD Pipeline DR Updates | helm-charts/scripts/mirror-base-images-to-ecr.sh | Modified | Region-aware mirror script (passes region as argument)
41 | 19. CI/CD Pipeline DR Updates | helm-charts/docker/services/Dockerfile.* (11 files) | Verified | ARG BASE_REGISTRY pattern verified DR-compatible across all services
42 | 19. CI/CD Pipeline DR Updates | helm-charts/docker/frontend/dockerfile | Verified | ARG BASE_REGISTRY pattern verified DR-compatible
43 | 19. CI/CD Pipeline DR Updates | helm-charts/docker/db-migration/Dockerfile.dbmigration | Verified | ARG BASE_REGISTRY pattern verified DR-compatible
44 | 19. CI/CD Pipeline DR Updates | helm-charts/health-aggregator/Dockerfile | Verified | ARG BASE_REGISTRY pattern verified DR-compatible
45 | 19. CI/CD Pipeline DR Updates | GitHub repo secrets | Added (manual) | AWS_ROLE_TO_ASSUME_PROD_DR, AWS_REGION_PROD_DR, ARGOCD_SERVER_PROD_DR, ARGOCD_AUTH_TOKEN_PROD_DR

## Apply Sequence
Phase | Action | Stack / Command | Region | Expected Outcome | Duration | Risk | Status
0 | Pre-flight: snapshot prod Aurora | aws rds create-db-cluster-snapshot --db-cluster-identifier prod-aurora-postgres ... | eu-west-1 | Manual snapshot created | 5–10 min | None | Manual
0 | Pre-flight: sync prod-dr DB secret to prod creds | aws secretsmanager update-secret --secret-id prod-dr/aurora/app-credentials ... | eu-central-1 | Secret matches prod's master creds | 1 min | None | Manual
1 | Apply: prod Aurora instance class | cd envs/prod/eu-west-1/aurora-postgres && terraform apply | eu-west-1 | Instances upgraded to db.r6g.large | 5–10 min (~60s blip) | Medium | Pending apply
2 | Apply: Prod EKS + logs EFS | cd envs/prod/eu-west-1/eks && terraform apply | eu-west-1 | Logs EFS + mount targets created | 5–10 min | Low | Applied
2 | Apply K8s: logs SC + PVC (prod) | kubectl apply -f envs/prod/eu-west-1/eks/k8s/efs-logs-*.yaml | eu-west-1 | PVC efs-logs-claim Bound | <1 min | None | Applied
3 | Apply: Aurora Global Cluster | cd envs/prod/eu-west-1/aurora-postgres-global && terraform apply | eu-west-1 | Global cluster created, adopts prod | 2–5 min | Low | Pending apply
4 | Apply: Prod-DR EKS (destroy old EFS, add logs EFS) | cd envs/prod-dr/eu-central-1/eks && terraform apply | eu-central-1 | Standalone data EFS gone, logs EFS created | 5–10 min | Medium | Applied
4 | Apply K8s: logs SC + PVC (prod-dr) | kubectl apply -f envs/prod-dr/eu-central-1/eks/k8s/efs-logs-*.yaml | eu-central-1 | PVC efs-logs-claim Bound | <1 min | None | Applied
5 | Apply: EFS Replication | cd envs/prod/eu-west-1/efs-replication && terraform apply | Both | Replica EFS auto-created in eu-central-1; replication ENABLED | 5–10 min | Low | Pending apply
6 | K8s: create Access Point on replica + apply static PV | aws efs create-access-point ... ; kubectl apply -f efs-pvc.yaml | eu-central-1 | PVC efs-claim Bound to static PV | 1–2 min | Low | Pending K8s apply
7 | Apply: Prod-DR Aurora → secondary | cd envs/prod-dr/eu-central-1/aurora-postgres && terraform apply | eu-central-1 | Standalone destroyed + recreated as global secondary | 15–25 min | Medium | Pending apply
8 | Apply: ACM Public Cert in prod-dr | cd envs/prod-dr/eu-central-1/acm/accesshub-identity && terraform apply | eu-central-1 | ACM cert ISSUED in eu-central-1 | 1–3 min | None | Pending apply
9 | ArgoCD: reconcile helm values (both regions) | argocd app sync ... | Both | Pods restart with new claimName | 2–5 min | Low | Applied
10 | End-to-end DR verification | Replication lag, proxy target health, PVC bindings, smoke test | Both | All green | 10–15 min | None | Pending

## Risk & Rollback
Workstream | Risk | Impact | Mitigation (pre-apply) | Rollback procedure
Prod Aurora instance class change | Writer failover blip >60s | Brief connection errors for active sessions | RDS Proxy + app retry logic | Re-apply with instance_class = db.t4g.medium
Aurora Global Cluster creation | Adoption fails (wrong source ARN) | Prod cluster unaffected | Verify cluster ARN via terraform plan | terraform destroy on aurora-postgres-global stack
Prod-DR Aurora cluster recreation | Plan shows unexpected destruction | Loss of supporting resources | Review plan carefully (expect only cluster + instances + proxy_target) | Restore from snapshot; re-apply
Prod-DR Aurora — credentials mismatch | RDS Proxy target stuck REGISTERING | Apps in prod-dr cannot authenticate via proxy | Pre-flight 0.2: sync prod-dr secret to match prod | Update secret; proxy auto-recovers in 60s
EFS Replication initial sync delay | Data lag | Pods may see incomplete files temporarily | Verify replication lag <1s | Wait for sync to catch up
Static PV — wrong Access Point path | Pods see empty subPath dirs | Init containers may fail with EROFS | Capture prod AP path BEFORE creating replica AP | Recreate replica AP with correct path; rollout restart
EFS logs PVC not applied | Pods stuck ContainerCreating | Deployment can't start | Apply efs-logs-pvc.yaml + SC before ArgoCD reconcile | kubectl apply missing manifests
ACM cert validation hangs | Cert stays PENDING_VALIDATION | Terraform apply blocks | Verify Route53 zone exists | terraform destroy; fix hosted_zone_name; re-apply
SIEM Firehose delivery failure | DeliveryToS3.Success < 1.0 | Audit logs lost | Verify bucket/KMS/IAM policies | Read Firehose error log group; fix IAM